## Sheet1
Swim Phone Redesign: Initial Price Estimates
| Min Hours | Max Hours | Price/Hour | Min Price |  | Max Price
Phase 1: Research (3 weeks)
User Interviews | 8 | 12 | 30 | $240.00 | - | $360.00
Competitive Analysis | 4 | 6 | 30 | $120.00 | - | $180.00
Personas Creation | 2 | 4 | 30 | $60.00 | - | $120.00
Creative Brief | 4 | 6 | 30 | $120.00 | - | $180.00
Lo-Fi Prototyping | 20 | 30 | 30 | $600.00 | - | $900.00
Requirements Gathering | 5 | 10 | 50 | $250.00 | - | $500.00
Phase 2: Design (4 weeks)
Development Consulting | 1 | 5 | 50 | $50.00 | - | $250.00
Hi-Fi Prototyping/Design | 50 | 70 | 30 | $1,500.00 | - | $2,100.00
User Testing | 20 | 40 | 30 | $600.00 | - | $1,200.00
Client Feedback | 5 | 15 | 30 | $150.00 | - | $450.00
Phase 3: Development (3 weeks)
Site Development | 30 | 40 | 50 | $1,500.00 | - | $2,000.00
Cross-Browser Testing | 1 | 2 | 50 | $50.00 | - | $100.00
Cross-Browser Fixing | 5 | 10 | 50 | $250.00 | - | $500.00
Client Feedback - Design | 1 | 10 | 30 | $30.00 | - | $300.00
User Testing | 2 | 5 | 30 | $60.00 | - | $150.00
Client Feedback - Dev | 1 | 5 | 50 | $50.00 | - | $250.00
Totals
| 159 | 270 |  | $5,630.00 | - | $9,540.00